## Tickets2018
TICKET ID | INCOMING DATE | RESPONSE FROM | COMPLETION DATE | RESOLUTION | SEVERITY | ORIGIN | STATUS
2018012304086250 | 2018-01-23 | asap.support | 2018-01-23 | Here the info requested: MSISDN, 2462342079 is not a valid msisdn on HLR NE. I executed the query using MSISDN, 12462342079 and the this number is associated to IMSI,342600202307464. | LOW | FLOW IT AUTOMATED PROVISIONING | FINISHED
Liberate Incident: 242750, Lime Ref: 4077211 -- REQUEST TO REMOVE/VERIFY AND CEASE | 2018-01-29 | asap.support | 2018-01-29 | The issue was reported last week, the connection is refused by the NE (EST_GSAT) during the handshake process. We require presence of the GOGSAT administrator. @Rhonda, Did you have some chance to contact the NE administrator? | MEDIUM | Rhonda | OPEN
2018012904099631 | 2018-01-29 | asap.support | 2018-01-30 | (SO_ID=5685985) The CAY_CS2K platform is not working properly. It is required to contact the NE administrator to know the root cause. Regarding to the (SO_ID=5684837) The specified DN 3459460986 has not been assigned to any subscriber. //It is not configured. | MEDIUM | IGATE LIBERATE TIER 2 SUPPORT | FINISHED
2018011504069587 | 2018-01-30 | asap.support | 2018-02-01 | We have several platforms, please for further requests it is required to send us the NE_ID parameter related on the switch message sent to know where to do the search those service numbers. We locate the service numbers in DOM_ROSE platform. Attached you can find the information related to those services. 17674491178 ACTIVE 17674486720 ACTIVE 17674485801 ACTIVE 17674481123 ACTIVE 17674484077 ACTIVE 17674407621 ACTIVE 17674456834 ACTIVE 17674485463 ACTIVE 17674454570 ACTIVE 17674484012 ACTIVE 17674481102 ACTIVE 17674402778 ACTIVE 17674409914 ACTIVE We require confirmation to remove/cease/delete manually the services of this platform. | LOW | Joy | FINISHED
2018020104107405 | 2018-02-02 | asap.support | 2018-02-02 | The session was locked on another device. It means that was received traffic for the same NE through both ASAP servers. We did the procedure to release the session. You can proceed with resubmission. Please let us know your results. | MEDIUM | Kishore | FINISHED
2018020104107405 | 2018-02-03 | asap.support | 2018-02-05 | Please transfer this request to FIXED team. The JAM_MYPN is out of sync. | LOW | Kishore | FINISHED
Liberate Incident : 242882, Lime Ref: 4093013 -- REMOVE SERVICE FROM NETWORK - GND BU | 2018-02-05 | asap.support | 2018-02-06 | Both Zimbra actrions where executed successfully. C-ZIMBRA_1_0_SUS_ACC COMPLETED 2018-Feb-05 02:37:49 PM C-ZIMBRA_1_0_DEL_ACC COMPLETED 2018-Feb-05 02:37:51 PM The subscriber is related to a centigram decommisioned platform (GND_HVML) please check the voicemail product code. C-CENTIGRAM_QNIX64_DEL_VMB TIMEOUT 2018-Feb-05 02:37:58 PM | LOW | Uday | FINISHED
2018020504115275 | 2018-02-06 | asap.support | 2018-02-07 | We found the following information on SKB_BAST platform. See further information in the attached file. | LOW | Praneetha | FINISHED
2018011504069587 | 2018-02-08 | asap.support | 2018-02-08 | Those command numbers are too old to be traced. We require the NE_ID that were used in the switch message to know where to find. We did a research on DOM_ROSE platform and most of those numbers are UNASSIGNED type. Further information on the attached file. | LOW | Joy | FINISHED
2018020604117503 | 2018-02-08 | asap.support | 2018-02-08 | Hi Leon, We did a research on AXA_VALL platform below the summary of the state. and attached you can find further information. BR | LOW | León | FINISHED
Liberate Incident : 242882, Lime Ref: 4093013 -- REMOVE SERVICE FROM NETWORK - GND BU | 2018-02-13 | asap.support | 2018-02-13 | Hi Uday, In the past Neilsa shares the below table, I cannot see the 10007 and 10008. @Neilsa, @Rhonda, Could you please confirm where should be mapped the mailboxes for GND_HVML? | MEDIUM | Uday | FINISHED
2018020804121550 | 2018-02-13 | asap.support | 2018-02-13 | Hi Shalana, Could ypu please provide us the Command number and Switch Messages related to the actions performed ? | LOW | Shalana | FINISHED
2018020504115275 | 2018-02-12 | asap.support | 2018-02-13 | Hi Praneetha, the following numbers were ceased on DMS: 8694651233 8694667877 8694654808 8694695790 The rest of the numbers on the list are of type VIRTUAL DIRECTORY NUMBER and they cannot be modified by provisioning; FIXED platform support can help with those numbers. | LOW | Praneetha | FINISHED
2018020804121550 | 2018-02-14 | asap.support | 2018-02-14 | We don't have access to Liberate's system, please share us the Command Number and the Switch message generated. Otherwise contact Liberate Support if the request was not generated properly. | LOW | Mark | FINISHED
Liberate Incident: 242750, Lime Ref: 4077211 -- REQUEST TO REMOVE/VERIFY AND CEASE | 2018-02-14 | asap.support | 2018-02-14 | Below, the communication parameters. The connectivity is rejected during the handshake process. | MEDIUM | Jason | FINISHED
Escalation Liberate Incident:239635 Lime Ref:#3605624--Service active in Switch | 2018-02-14 | asap.support | 2018-02-14 | Happy Valentine's Day! We are not able to configure the LEN's provided into the platform . | LOW | Joy | FINISHED
2018013004101252 | 2018-02-14 | asap.support | 2018-02-14 | Hello, Praneetha; We have this information in ASAP: At 085025 on MCLI = SKB_HUAW, with IMPU = sip:+18694660999@softswitch.lime.com, an OwedRestriction/IncomingCallRestriction was applied and Operation succeeded. Then at 085027 on MCLI = SKB_HUAW, with IMPU = sip:+18694660999@softswitch.lime.com, an OwedRestriction/OutgoingCallRestriction was applied and Operation succeeded. Then both Incoming and Outgoung call restrictions were applied to the subscriber. This is the Info retrieved from the switch: <m:complete-communication-barring> <m:incoming-communication-barring active="true"><m:ruleset></m:ruleset> </m:incoming-communication-barring> <m:outgoing-communication-barring active="true"><m:ruleset></m:ruleset> </m:outgoing-communication-barring> <m:operator-incoming-communication-barring authorized="true"></m:operator-incoming-communication-barring> <m:operator-outgoing-communication-barring authorized="true"></m:operator-outgoing-communication-barring> </m:complete-communication-barring> <m:OwedRestriction><m:IncomingCallRestriction> <m:ToneID>3</m:ToneID> </m:IncomingCallRestriction> <m:OutgoingCallRestriction><m:ToneID>14</m:ToneID><m:ContinueAfterPlayTone>0</m:ContinueAfterPlayTone> </m:OutgoingCallRestriction> </m:OwedRestriction> Please find attached the complete subscriber's configuration. 15-02-18 According to ASAP records, call restrictions were applied on february 14th, 2018 at 08:50 hrs. | LOW | Praneetha | Finished
Advise on Failure of Service Order | 2018-02-14 | asap.support | 2018-02-14 | Hi Joy, The Service number is UNASSIGNED. BR | LOW | Joy | FINISHED
Service Not Ceased at Switch | 2018-02-14 | asap.support | 2018-02-14 | Could you please provide us the Command number and Switch message sent to verify the actual status for the service number?. We can see that you got "NO REQUEST" response, please ask to Liberate support why the command and the message was not generated. | LOW | Joy | FINISHED
Calls In suspense - 9048402 | 2018-02-15 | asap.support | 2018-02-15 | Hi Joy. ASAP can reach the JAM_CALIX NE, but cannot start session. CMS 18-02-15 10:12:05^M A 5138 REPT EVT SECU^M "sysadmin:LOGINFAIL,TC,02-15,10-12-05:N1-1-MS-E3,\"RepeatLogin\""^M ;^M | MEDIUM | Joy | FINISHED
Jamaica Weekly Switch Failure Report-14-FEB-2018 | 2018-02-15 | asap.support | 2018-02-15 | Checks show for failure #1 SO_FAILURE:ERR_CODE=Already connected; that 493 failed records were generated for service # 8817878. Please advise on the reason for this switch failure and why 493 records when switch screen on Liberate shows a total of 8 records. Activation service was intermittent on JAM_CVVM (feb 13th, from around 4:54 hrs to 6:50 hrs). There were response codes: 401 from the NE and after this, the "Already connected" message appeared when reconnection was tried. At 6:50 hrs on feb 13th, activation service was restablisehd with JAM_CVVM. | MEDIUM | Joy | FINISHED
Jamaica Weekly Switch Failure Report-14-FEB-2018 | 2018-02-16 | asap.support | 2018-02-16 | Could you please send us the last command number and the switch message sent for each number to do a follow up for those service numbers? | LOW | Joy | FINISHED
2018021704140526 | 2018-02-20 | asap.support | 2018-02-20 | The comands related to "src=radius" do not belongs to ASAP platforms. | LOW | Praneetha | FINISHED
2018021904142062 | 2018-02-20 | asap.support | 2018-02-20 | The subscribers are related an old voice mail product code linked to SLU_CVML. The SLU_CVML is a decommisioned platform. | LOW | Chinnasani | FINISHED
2018021804141509 | 2018-02-20 | asap.support | 2018-02-20 | The work order fails during an internal search for the submcli; executing the following select command. select submcli from tbl_dnrange_submcli where 9791032 between from_dn and to_dn and submcli = 'JAM_MOBY' The range belongs to JAM_MOBYJ SUBMCLI FROM_DN TO_DN VOICEMAIL_DN JAM_MOBYJ 9790000 9793999 19801999 JAM_DGPT 9798000 9798999 19801999 JAM_MOBYJ 9795000 9797999 19801999 JAM_MOBYJ 9799000 9799999 19801999 JAM_SIGN 9794000 9794999 19801999 The ranges that belongs to JAM_MOBY are the following. SUBMCLI FROM_DN TO_DN VOICEMAIL_DN JAM_MOBY 6300000 6309999 19802999 JAM_MOBY 6310000 6319999 19802999 JAM_MOBY 6330000 6339999 19802999 JAM_MOBY 6320000 6329999 19802999 JAM_MOBY 6200000 6209999 19802999 JAM_MOBY 9212067 9212067 19801999 JAM_MOBY 6220000 6229999 19802999 JAM_MOBY 6650000 6659999 19801999 JAM_MOBY 6670000 6679999 19801999 JAM_MOBY 6690000 6699999 19801999 JAM_MOBY 6060000 6069999 19802999 JAM_MOBY 6680000 6689999 19801999 JAM_MOBY 6180000 6189999 19802999 JAM_MOBY 6190000 6199999 19801999 JAM_MOBY 6480000 6489999 19801999 JAM_MOBY 6490000 6499999 19801999 Could you please retry the WO using JAM_MOBYJ? | MEDIUM | Praneetha | FINISHED
IP Address Change - Huawei MSAN | 2018-02-20 | asap.support | 2018-02-20 | Thank you Rhonda, Mora, We encounter three more DSLAM_IDs used in some Work orders. Mora, Could you please provide us the related IP address? Thank you in advance. BR | LOW | Mora | OPEN
2018021904142421 | 2018-02-21 | asap.support | 2018-02-21 | The command number was completed successfully. CIS:GND:5232110:172.21.64.14:25004:1519 337614 COMPLETED 2018-Feb-20 10:49:52 AM 2018-Feb-20 10:50:42 AM 2018-Feb-20 10:51:06 AM The subscriber configuration below: INT::DN:GND_HART 4989269 INFO.001 qdn 4436586 INT::DN:GND_HART 4989269 INFO.002 ----------------------------------- INT::DN:GND_HART 4989269 INFO.003 DN: 4436586 INT::DN:GND_HART 4989269 INFO.004 TYPE: SINGLE PARTY LINE INT::DN:GND_HART 4989269 INFO.005 SNPA: 473 SIG: DT LNATTIDX: 29 INT::DN:GND_HART 4989269 INFO.006 LINE EQUIPMENT NUMBER: CCOU 01 INT::DN:GND_HART 4989269 INFO.007 LINE CLASS CODE: 1FR INT::DN:GND_HART 4989269 INFO.008 IBN TYPE: STATION INT::DN:GND_HART 4989269 INFO.009 CUSTGRP: RESGRP SUBGRP: INT::DN:GND_HART 4989269 INFO.010 LINE TREATMENT GROUP: 29 INT::DN:GND_HART 4989269 INFO.011 CARDCODE: 6X17AC GND: N PADGRP INT::DN:GND_HART 4989269 INFO.012 PM NODE NUMBER : 114 INT::DN:GND_HART 4989269 INFO.013 PM TERMINAL NUMBER : 109 INT::DN:GND_HART 4989269 INFO.014 OPTIONS: INT::DN:GND_HART 4989269 INFO.015 LCDR DGT NAME PUBLIC C CUDJOE INT::DN:GND_HART 4989269 INFO.016 RES OPTIONS: INT::DN:GND_HART 4989269 INFO.017 ACB AMA AR AMA INT::DN:GND_HART 4989269 INFO.018 ----------------------------------- INT::DN:GND_HART A-DMS100_NA14_QUERY_DN INFO SUCCEED BR | LOW | Samantha | FINISHED
Huawei MSAN ASAP ADD-SERVICEPORT request query. | 2018-02-22 | asap.support | 2018-02-22 | Prakash, The request do not mention which parameter is missing or invalid, we tried to find an order completed but do not exist. Attached the ASAP'S log. | MEDIUM | Prakash | FINISHED | 2:00 PM
¦SR1585469¦ B2B - APN SEETINGS TO BE REMOVED FROM 2462311969 - A/C: 30135339 - MGM COMPANY LTD | 2018-02-22 | asap.support | 2018-02-22 | Nola, Could you please open a ticket Routed to Desktop Support Staff: Rasheing Graham, Stephnie Harrison on the group JAMAICA IT DESKTOP SUPPORT and they do a Browser configuration to work with OCA. Also, if you can send me your IP address to do a simple ping from WASS to ensure is not a networking problem Neilsa, We could set NAM=1 but we coudn't set PDPCP. Is it linked with another feature? Thanks in advance. BR | LOW | Nola | FINISHED
¦SR1585469¦ B2B - APN SEETINGS TO BE REMOVED FROM 2462311969 - A/C: 30135339 - MGM COMPANY LTD | 2018-02-22 | asap.support | 2018-02-22 | Nola, Please ensure to add in the ticket that your host is not reachable from WASS1133. BR [-] /asap/app/asap/asappro1 ==>$ hostname wass1133.cwwi.cwintra.com [-] /asap/app/asap/asappro1 ==>$ /usr/sbin/ping 172.20.102.94 no answer from 172.20.102.94 | LOW | Nola | FINISHED
Resetting of ASAP-WASS1133 OCA Passwords | 2018-02-22 | asap.support | 2018-02-22 | The accounts neilsa, nola, kenny have the password welcome1 | LOW | Neilsa | FINISHED
CEC_ APN verification | 2018-02-22 | asap.support | 2018-02-22 | Below the subscriber configuration. Something caught our attention. The subscriber is not present on AUC and HSS | LOW | Neilsa | FINISHED
Liberate Incident: 243142, Lime Ref: 4137088-- Switch failure | 2018-02-21 | asap.support | 2018-02-26 | Could you please retry this request on WASS server? | LOW | Kishore | FINISHED
2018022104147238 | 2018-02-23 | asap.support | 2018-02-23 | SO_ID 177494042 timed out on jamu66 as there were connection failures to HUAW NE: CIS:JAM:177494042:172.21.64.17:25007:15 350417 TIME_OUT 2018-Feb-21 10:04:37 AM 2018-Feb-21 10:04:38 AM Please resend it to wass1133 and send all HUAW activation requests to wass1133 ASAP server, except for bulks greater than 100 numbers as per Neilsa instructions, during this period with jamu66 offline and wass1133 on observation. | LOW | Kishore | FINISHED
Liberate Incident: 243142, Lime Ref: 4137088-- Switch failure | 2018-02-27 | asap.support | 2018-02-27 | Response from NE JAM_CVVM contains two error messages: NGVM_ETTY_DSNT_EXST: The specified Mailbox ID does not exist on the Comverse Voicemail platform. And second one is consecuence of the first one: NGVM_MIPS_DATASTR: The MIPS returned a datastore error. | LOW | Chinnasani | FINISHED
Fw: Mobile Details | 2018-02-27 | asap.support | 2018-02-27 | Hi Neilsa, Janelle, we could not find information related to those IMSI numbers: 342600201619188 342600201840222 HLRSUB:IMSI,342600201619188; RESP:13; The Specified IMSI is not defined HLRSUB:IMSI,342600201840222; RESP:13; The Specified IMSI is not defined LIMESUB:IMSI,342600201840222; RESP:35106; The subscriber does not exist LIMESUB:IMSI,342600201619188; RESP:35106; The subscriber does not exist | LOW | Neilsa | FINISHED
The Help Desk Task 2018022704159605 has been routed to the CIS SUPPORT (LONDON) queue with status New. | 2018-02-28 | asap.support | 2018-02-28 | This issue is caused by a connection failure of the main provisioning user to the ASAP platform, all NEs using server wass1133 as intermediate connection are being affected. We have already reported this problem to the sysadmins. We'll let you known when it is solved. Best regards. | MEDIUM | Kishore | FINISHED
The Help Desk Task 2018022704159309 has been routed to the CIS SUPPORT (LONDON) queue with status New. | 2018-02-28 | asap.support | 2018-02-28 | Hi Praneetha, this is the subscriber's information on DMS switch. | LOW | Praneetha | FINISHED
2018022704159519 | 2018-02-28 | asap.support | 2018-02-28 | This issue is caused by a connection failure of the main provisioning user to the ASAP platform, all NEs using server wass1133 as intermediate connection are being affected. We have already reported this problem to the sysadmins. We'll let you known when it is solved. | MEDIUM | Samantha | FINISHED
2018022804160817 | 2018-02-28 | asap.support | 2018-02-28 | We noticed that most of the requests has been processed. If another request caused timeout, please retry. Thank you. | MEDIUM | Kishore | FINISHED
High Priority Switch requests stuck in started status | 2018-02-28 | asap.support | 2018-02-28 | A password change by the password management system. | MEDIUM | kishore | FINISHED
Bulk Sim provisioning | 2018-02-28 | asap.support | 2018-02-28 | SO_FAILURE:ERR_CODE=No such file or directory; Is a SAPC response message, the order failed due to a connection device failure, device did not release the session and ldap resources for SAPC where not available for that device's session. SAPC command is the last command on the order to be executed, then order is partially completed, only creation on SAPC is missing. | MEDIUM | Kishore | FINISHED
Cayman ASAP Switch Requests - Time Out | 2018-02-28 | asap.support | 2018-02-28 | Currently all request for Cayman Genband CAY_GNBND are timed out, there is no connection to NE from the ASAP server on the cloud, only jamu66 ASAP can connect but it is offline due to a hardware failure. This connection issues to Genband host are already reported; As soon as jamu ASAP environment is back online, we'll regain connection to the NE and requests can be resubmitted. | MEDIUM | Wendy | FINISHED
SLU_Cast ASAP port down | 2018-02-28 | asap.support | 2018-02-28 | SLU_CEN and SLU_UVF are working properly. | LOW | Terry | FINISHED
Quick Assistance Needed! | 2018-03-01 | asap.support |  | CREATE:AUCSUB:IMSI,342600202139334:KI,7962C6ECA3F61187E99318BCC7F8FCE3:AD,0:ADKEY,7:A38,2; CREATE:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:PDPCP,2; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:TS11,1; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:OBR,2; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:REGSER,3; SET:HLRSUB:MSISDN,12462335899:OFA,2; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:RSA,32; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:NAM,0; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:CFB,1,1,17582850000,TS10; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:CFNRC,1,1,17582850000,TS10; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:CFNRY,1,1,17582850000,TS10; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:CFU,1,0,17582850000; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:HOLD,1; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:CAW,1,1; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:CLIP,1; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:SOCLIR,2; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:CLIR,1; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:OBR,0; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:REGSER,0; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:MPTY,1; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:TS22,1; SET:HLRSUB:MSISDN,12462335899:IMSI,342600202139334:TS21,1; | LOW | Neilsa | OPEN
REquests getting stuck | 2018-03-05 | asap.support | 2018-03-05 | Ok, I included the info when I found the request Kishore provided us (SO_ID=178017432) timed out for the CMV common service. CIS:JAM:178017432:172.21.64.17:25007:1520258399645 2018-Mar-05 09:00:01 AM 126138 TIME_OUT CMV_CARL And there are more similar requests. Those requests timing out are known issue We do not see other requests from other platforms on time out status. | LOW | Neilsa, Kishore | FINISHED
Liberate Incident: 242750, Lime Ref: 4077211 -- REQUEST TO REMOVE/VERIFY AND CEASE | 2018-03-06 | asap.support | 2018-03-06 | URIs from all JAM, BAR and EST GSAT are reachable from their URLs but there is no authorization to connect from ASAP environments, connection fails at protocol's handshake phase. | LOW | Neilsa, Chinnasani | FINISHED
RE | 2018-03-08 | asap.support | 2018-03-08 | Hi Barbara, The password for JAMU is now Welcome2- Please retry and let us know. Thanks and regards | LOW | Barbara | FINISHED
Liberate Incident:243422--Auto Cease CEL/CES Issue | 2018-03-08 | asap.support | 2018-03-08 | Here the info from the DOM_ROSE switch: DN: 4482324 LINE EQUIPMENT NUMBER: GDWL 00 0 02 28 | LOW | Chinnasani | FINISHED
Liberate Incident:243451 Lime Ref:#4172444--CEF REMOVAL FAILING IN SWITCH FOR TELEPHONE # 443-8309 | 2018-03-08 | asap.support | 2018-03-08 | According to Common service parameters for GATE_SS_MOD_ACC_SET, ACCOUNT_NAME is a mandatory parameter: COMMGATE_4_2_MOD_ACC_SET 1 NE_ID Required COMMGATE_4_2_MOD_ACC_SET 2 ACCOUNT_NAME Required And in SO_TYPE request, it is not provided: ...CC_SET;NE_ID=BAR_COMG;ACCOUNT_NAME=;SETTINGS.PORT_LIMIT=1;SETTINGS.NAS_IP_ADDRES... | LOW | Chinnasani | FINISHED
Liberate Incident: 243460 Lime Ref:#4166961 -- ERROR IN THE SWITCH FOR RECONNECTION - 952-9309- Unable to make calls | 2018-03-08 | asap.support | 2018-03-08 | order with command number 178128185 was not completed: CIS:JAM:178128185:172.21.64.17:25007:1520407206622 141137 FAILED 2018-Mar-07 02:20:06 AM 2018-Mar-07 11:20:07 AM 2018-Mar-07 11:20:44 AM Reason was NE got out of synch: waitfor(): cltg $ 0 9529309 $ yCOMMAND AS ENTERED: CLTG NOW 18 3 7 AM 0 ( 9529309 ) $ MACHINES ARE OUT OF SYNC, SERVICE ORDERS NOT ALLOWED SHOULD ORDER BE DONE ANYWAY? (Y OR N) Please contact Fixed Support team, they can help with this issue. | LOW | Madhusudhan | FINISHED
Switch Failure - 4446502 - 4446502 GND BU | 2018-03-08 | asap.support | 2018-03-08 | Here's the subscriber's info from the switch: DN: 4446502 LINE EQUIPMENT NUMBER: STDV 00 0 04 28 Best regards. | LOW | Joy | FINISHED
ISP Email Provisioning Account - Jamaica | 2018-03-12 | asap.support | 2018-03-12 | here the info from ASAP comm parameters: NE_ID Administrator User ANU_GOOG asapprovisioning@candw.ag AXA_GOOG asapprovisioning@anguillanet.com BAR_GOOG asapprovisioning@caribsurf.com BVI_GOOG asapprovisioning@surfbvi.com DOM_GOOG asapprovisioning@cwdom.dm GND_GOOG asapprovisioning@spiceisle.com JAM_GOOG asapprovisioning@cwjamaica.com MNI_GOOG asapprovisioning@candw.ms SKB_GOOG asapprovisioning@sisterisles.kn SLU_GOOG asapprovisioning@candw.lc SVD_GOOG asapprovisioning@vincysurf.com TKI_GOOG asapprovisioning@tciway.tc And NE_ID Neonova user: ANU_ZBRA asapadmin@candw.ag AXA_ZBRA asapadmin@anguillanet.com BAR_ZBRA asapadmin@caribsurf.com BVI_ZBRA asapadmin@surfbvi.com CAY_ZBRA asapadmin@candw.ky DOM_ZBRA asapadmin@cwdom.dm GND_ZBRA asapadmin@spiceisle.com JAM_ZBR2 asapadmin@cwjamaica.com JAM_ZBRA asapadmin@cwjamaica.com MNI_ZBRA asapadmin@candw.ms SKB_ZBRA asapadmin@sisterisles.kn SLU_ZBRA asapadmin@candw.lc SVD_ZBRA asapadmin@vincysurf.com TKI_ZBRA asapadmin@tciway.tc Hope this helps. | LOW | Neilsa | FINISHED
RE: | 2018-03-13 | asap.support | 2018-03-13 | Hi Barbara, the acount was locked out, would you please try with: BARBARA/Welcome2- Best regards. | LOW | Barbara | FINISHED
Data Call In Suspense - 5371639 | 2018-03-14 | asap.support | 2018-03-14 | The subscriber (18765371639, IMSI=338180111275012 ) Does not exist on the platforms HLR, HSS, SAPC nor CVVM. | LOW | Joy | FINISHED
Mobile Ceased But still Making SMS | 2018-03-14 | asap.support | 2018-03-14 | The subscriber (18769994577, 338180102321562) Does not exist on the platforms HLR, HSS, SAPC nor CVVM. | LOW | Joy | FINISHED
CCN-4111 - Caribbean Broilers Group Vehicle Tracking APN - JAMAICA | 2018-03-19 | asap.support | 2018-03-19 | The MSISDN=18090063 is incomplete, Could you please retry the request adding the country code in the parameter? Please let us know your results. | LOW | Pradeep | FINISHED
Unexpected Rejection of Switch Request | 2018-03-20 | asap.support | 2018-03-20 | We found a complete example, attached you can find the txt. The sequence used that fails is: C-EMA_6_2_CREATE_IMSI C-EMA_6_2_CREATE_IMSICH C-EMA_6_2_ADD_CAMELPROFILE C-EMA_6_2_ADD_HSSSUBSCRIPTIONID The sequence that should be used is: C-EMA_6_2_CREATE_IMSI C-EMA_6_2_CREATE_IMSICH C-EMA_6_2_ADD_CAMELPROFILE C-EMA_6_2_MOD_HSSSUBSCRIPTION (GET, DELETE, CREATE) The Modify previoulsy delete the information related to the old IMSI. We don't know the OLD_IMSI value to send a query or delete. Please let us know your results. | LOW | Neilsa | FINISHED
Testing Data Subscriptions with New SAPC Profile_IDs | 2018-03-20 | asap.support | 2018-03-20 | According to the logs, the problem was with the subscription date: "subscriptionDate":"19-02-2018T23:59:59" ldap_add: Invalid syntax ldap_add: additional info: Validation error in 'EPC-Data': subscriptionDate + re setPeriod must be a date in the future in /Reporting Group[2200] field C-ERICSAPC_3_0_ADD_P A-ERICSAPC_3_0_ADD_P MSISDN 18768162734 C-ERICSAPC_3_0_ADD_P A-ERICSAPC_3_0_ADD_P SUBSCRIPTION_DATE 19-02-2018T23:59:59 C-ERICSAPC_3_0_ADD_P A-ERICSAPC_3_0_ADD_P SUBSCRIPTION_DATE 19-02-2018T23:59:59 Best regards. | LOW | Neilsa | FINISHED
Failure Message Not Generate W.r.t. BAR_SAPC Switch Requests | 2018-03-20 | asap.support | 2018-03-20 | We modified the user error table to fix the exit type, now ASAP will respond like this: INFO ASDL Exit (FAIL) Msg : ldap_simple_bind: Can't connect to the LDAP server - Connection refused. Best regards. | MEDIUM | Neilsa | FINISHED
Failed Query | 2018-03-20 | asap.support | 2018-03-20 | The WO was completed CIS:JAM:178535568, the subscriber was created with the information provided but was deleted with the WO CIS:JAM:178536202. The subscriber currently does not exist. It was used the addPostpaidSubscriber() method. This method just do the validation for the parameters voLimitUp, notLev1 and notLev2 to be not NULL or blank space. Because for this particular case the volume limit should be voLimit = notLev1 + "," + notLev2 + "," + voLimitUp; as result = 1572864,1992294,2097152 We couldn't see the local allotment of 3GB and a roaming allotment of 500MB With profile_id =I 100. Was it another WO_ID ? | LOW | Neilsa | FINISHED
JAM 10 digit service number testing error for POTS fixed line provisioning. | 2018-03-21 | asap.support | 2018-03-21 | ASAP accepts DN with 7 or 10 digits, problem is with the submcli table (used to route requests to the proper POTS host) , where DN ranges are still defined with 7 digits: Then DN ranges must be updated in that table. | LOW | Prackash | FINISHED
Requesting the SO-ERICSAPC_SS_DEL_SUBSCRIBER Code/Logic Be Examined - URGENT | 2018-03-21 | asap.support | 2018-03-21 | NE_LDAP restart | MEDIUM | Neilsa | FINISHED
Unexpected Rejection of Switch Request | 2018-03-20 | asap.support |  | When a MSISDN is brand new, the MOD_HSS will fail because there is no pre-existing HSS subscription. | MEDIUM | Neilsa | FINISHED
Testing Data Subscriptions with New SAPC Profile_IDs | 2018-03-20 | asap.support | 2018-03-20 | "subscriptionDate":"19-02-2018T23:59:59" ldap_add: Invalid syntax ldap_add: additional info: Validation error in 'EPC-Data': subscriptionDate + re setPeriod must be a date in the future in /Reporting Group[2200] field C-ERICSAPC_3_0_ADD_P A-ERICSAPC_3_0_ADD_P MSISDN 18768162734 C-ERICSAPC_3_0_ADD_P A-ERICSAPC_3_0_ADD_P SUBSCRIPTION_DATE 19-02-2018T23:59:59 C-ERICSAPC_3_0_ADD_P A-ERICSAPC_3_0_ADD_P SUBSCRIPTION_DATE 19-02-2018T23:59:59 | LOW | Neilsa | FINISHED
Failure Message Not Generate W.r.t. BAR_SAPC Switch Requests | 2018-03-20 | asap.support | 2018-03-20 | Would you please insert the value of the relevant NE_ID in that message? e.g. INFO ASDL Exit (FAIL) Msg : ldap_simple_bind: Can't connect to the LDAP server - Connection refused for <ne_id>. | LOW | Neilsa | FINISHED
JAM 10 digit service number testing error for POTS fixed line provisioning. | 2018-03-21 | asap.support | 2018-03-25 | The 876* dn_ranges were added. Just six numbers does not belongs to any of the 5942 configured ranges (876-612-3403, 876-627-9335, 876-627-9336, 876-627-9337, 876-627-9338, 876-627-9339) Similarly all the 658* does not belongs to the configured ranges. If someone knows the submcli where they belongs they can be added. Neilsa, We did de comparison between JAMU and WASS ten records are inconsistent. The missing ones can be added to the another table but, We are going to require confirmation between the duplicated and not similar. | MEDIUM | Prakash | FINISHED
ASAP - SAPC delete subscriber logic issue. | 2018-03-22 | asap.support | 2018-03-22 | If the resultant RM_VOLUME_LIMIT = 0, then only the Local / Home allotment should be deleted. Similarly, if the resultant DEC_RM_VOLUME_LIMIT = 0, then only the roaming allotment should be deleted. | MEDIUM | Neilsa | FINISHED
Weird Processing by JAMU66 | 2018-03-23 | asap.support | 2018-03-23 | The SAPC cartridge is not able to manage an order containing BOLT_ON_FLAG=5, DEC_RM_VOLUME_LIMIT and ROAM_FLAG=1 parameters when subscriber does not have any roaming allotment: Work Order ID is : CIS:JAM:178622158:172.21.64.17:25007:1521836421157 {BOLT_ON_FLAG=5, DEC_RM_VOLUME_LIMIT=512000, SO_TYPE=SO-ERICSAPC_SS_DEL_SUBSCRIBER, ROAM_FLAG=1, NE_ID=JAM_SC14B, MSISDN=18768163994, DEC_RM_CAPPED_LIMIT=0} | MEDIUM | Neilsa | FINISHED
new 876 fixed line provisioned | 2018-03-28 | asap.support | 2018-03-28 | Attached you can find the requested logs. The first case regarding to the service number DMS100 (9687477) is actually type unnasigned we couldn't find the request. Regarding to the case DMS100 (8769681084) without the prefix 'DSL' is properly processed and accepted for the Network Element and ASAP. Regarding to the case DSLAM (DSL8769681084) is necesary to verify the cartridge internally. As soon as we get the analysis we will inform you. | MEDIUM | Suresh | FINISHED
2018040404223215 | 2018-04-04 | asap.support | 2018-04-04 | We've already reported this issue, as soon as we get response we'll let you know when it is fixed to resend the orders. | MEDIUM | Chinnasanni | FINISHED
DOM ASAP requests failing with INCORRECT_SO_SIZE: Message size does not match message length provided | 2018-04-04 | asap.support | 2018-04-04 | The requests are being sent containing unknown characters thats why the SAIF application can't build the ASAP request properly. Please verify your system DOM 172.21.64.4 Please find attached the SAIF logs where you can see those characters. "^@^@^@^@^@^@^@^@^@^....." Please let us know your findings. | LOW | Prakash | FINISHED
DOM ASAP requests failing with INCORRECT_SO_SIZE: Message size does not match message length provided | 2018-04-05 | asap.support | 2018-04-05 | We also think that is a TCP/IP issue. Requests from all BU's are being processed by the same SAIF instance and they are not limited by length. You can retry to resubmit those requests. Much better if you can close and reopen a new socket session. | LOW | Mark | FINISHED
JAM 10 digit service number (658) testing error for SONUS fixed line provisioning. | 2018-04-10 | asap.support | 2018-04-10 | ASAP is receiving and error code 26 from NE, a parameter value is not properly defined in the order, the Error Message is "Directory Number number block not specified". NE does not have defined a numbers block including this DN. Also, could you please help us to define the ranges for 658-DNs to be included on ASAP NEP tbl_dnrange_submcli? | LOW | Suresh | FINISHED
JAM 10 digit service number testing error for POTS fixed line provisioning. | 2018-04-10 | asap.support | 2018-04-10 | The table that should be updated is from ASAP, called "tbl_dnrange_submcli" That table must be populated with the following data per row. SUBMCLI, FROM_DN, TO_DN, VOICEMAIL_DN. If you can provide us the requested information we can add those ranges. | LOW | Suresh | FINISHED
new 876 fixed line provisioned | 2018-04-10 | asap.support | 2018-04-10 | Hi Suresh, it will be necessary to ask Fixed team if DMS100 is able to handle a 10 digits length DN in its response. | LOW | Suresh | FINISHED
Two Questions ... | 2018-04-12 | asap.support | 2018-04-12 | DN ranges updated cartridge verification | MEDIUM | Neilsa | FINISHED
Fw: Carol Hamilton-rose shared "658 Test Numbers to be set up v2 (2)" with you. | 2018-04-12 | asap.support | 2018-04-12 | DN ranges updated | MEDIUM | Neilsa | FINISHED
BVI - Huawei ASAP error | 2018-04-13 | asap.support | 2018-04-13 | The error is obtained when SAIF maps the parameters for the POTS request. (Below in red) Is the action related to the MSAN activities? | LOW | Prakash | FINISHED
Fw: SO_FAILURE:ERR_CODE=Invalid DN Entered; for <6582950100> | 2018-04-13 | asap.support | 2018-04-13 | DN 6582950100 was not accepted by JAM_CAR3, | LOW | Neilsa | FINISHED
Size of TYPECODE Field? | 2018-04-16 | asap.support | 2018-04-18 | The fieldsize below. SUBMCLI VARCHAR2(10 BYTE) TYPECODE VARCHAR2(5 BYTE) LATTIX VARCHAR2(3 BYTE) DESCRIPTION VARCHAR2(20 BYTE) | MEDIUM | Neilsa | FINISHED
Liberate Incident: 244016, Lime Ref: 4230765 -- CHANGE 4480760/DS4480760 TO WORKING | 2018-04-16 | asap.support | 2018-04-16 | Could you please transfer this request to FIXED team to know why the Network element (DMS100 DOM_ROSE) returned the below response? | LOW | Neilsa | FINISHED
Getting Ready to Resubmit ... | 2018-04-18 | asap.support | 2018-04-18 | Here the command: DMS100 command for feature AddSingleLineJAM: | LOW | Neilsa | FINISHED
Rejected CARL Switch Command for 658nnnxxxx Service | 2018-04-18 | asap.support | 2018-04-18 | Table updated | LOW | Neilsa | FINISHED
876 10 Digit Service Activation on Liberate (Fixed & Mobile) for April 25, 2018 | 2018-04-26 | asap.support | 2018-04-26 | Suresh the subscriber does not have information related on the AUC. | LOW | Neilsa | FINISHED
Service Amendment to Create Voxgen Data | 2018-04-26 | asap.support | 2018-04-26 | The table DNRANGE_SUBMCLI should be updated with the corresponding ranges for the 658. Below the present configuration for JAM_CAR3 | LOW | Neilsa | FINISHED
CAY C20 /GENBAND ASAP requests | 2018-04-26 | asap.support | 2018-04-26 | The work order fails because the LEN SIP0 01 3 05 20 is associated with DN 9490689 Attached you can find the logs, | LOW | Prakash | FINISHED
The Help Desk task 2018041904249671 has been assigned to group CIS SUPPORT (LONDON) | 2018-04-26 | asap.support | 2018-04-26 | Comverse _CVVM switches have been working fine, could you please provide us with the command numbers to check the orders are not trying to activate services on decommisioned platforms. | LOW | Rhonda | FINISHED
Provision 10 Digit 876 Service Number from CARL | 2018-05-02 | asap.support | 2018-05-02 | The DN=8769080014 does not belongs to the ranges configured on DNRANGE_SUBMCLI. Below the actual ranges . | LOW | Neilsa | FINISHED
Fw: Action required: Upcoming Change to SSL Certificates for BlackBerry Provisioning System - Cable and Wireless Group (Caribbean) | 2018-05-02 | asap.support | 2018-05-22 | We've verified these new certificates, they seem to be correct. | MEDIUM | Neilsa | FINISHED
Failed switch Requests - GND BU | 2018-05-02 | asap.support | 2018-05-02 | The DN 4403309 is type VIRTUAL DIRECTORY NUMBER Please contact to the FIXED team what can be done for this type. The DN 4443936 is type SINGLE PARTY LINE and its related LEN is HOST 00 1 01 05. The DN 4446502 is type SINGLE PARTY LINE and its related LEN is STDV 00 0 04 28. Please contact to Liberate team to update both related LEN. | LOW | Joy | FINISHED
JAM 10 digit NPA request failure | 2018-05-09 | asap.support | 2018-05-09 | Attached you can find the requested logs. We did a qry with the provided information and the response retrieved is "The device does not exist" | LOW | Prakash | FINISHED
SIMA ASAP cartridge - has this been installed on JAMU66 and WAS133 ASAP servers | 2018-05-09 | asap.support |  |  | MEDIUM | Prakash | OPEN
TKI - HUAWEI_SS_MOD_SUB command failing | 2018-05-10 | asap.support | 2018-05-10 | The CALL_SOURCE_CODE is mandatory by the NE. You can see the requested log and a MOD_SUB completed with the CALL_SOURCE_CODE. | LOW | Prakash | FINISHED
Following-up on SR2051002 | 2018-05-10 | asap.support | 2018-05-10 | The activity was completed. Below the current configurations. | LOW | Neilsa | FINISHED
SIMA request query | 2018-05-10 | asap.support | 2018-05-10 | Attached you can find the requested log | LOW | Prakash | FINISHED
Numbers migrated from WEST 1 NEAX to WEST2 DMS Exchange | 2018-05-10 | asap.support | 2018-05-11 | The ranges are available to use on both ASAP servers. | MEDIUM | Neilsa | FINISHED
2018051504293394 | 2018-05-15 | asap.support | 2018-05-15 | We notice that most of the command numbers are linked to a decommisioned platform JAM_PROG PROGENY. Some other command numbers tried to communicate with DMS100 and JAM_PROG; the delay created with progeny stucked some devices. We are working to release those devices. | MEDIUM | Kishore | FINISHED
Error Switch request - 18769680007 | 2018-05-21 | asap.support | 2018-05-21 | ASAP platform requires the request generated. Please ask for some help to Liberate Support. | LOW | Joy | FINISHED
Failed Switch request - 9200089 | 2018-05-21 | asap.support | 2018-05-21 | Could you please proceed with the resubmission of the request? The history is not available for analysis. | LOW | Joy | FINISHED
Liberate Incident: 244663, Lime Ref:4303192-- Huawei orders stuck on started | 2018-05-21 | asap.support | 2018-05-21 | JAM_VERSO is not reachable for any ASAP server, Could you please help us to reach the fixed team to know the health of this NE ? | HIGH | Kishore | FINISHED
Switch request failures on JAM | 2018-05-25 | asap.support | 2018-05-25 | the actual error retrieved from NE is "<errorCode>473</errorCode><errorMessage>PIN already exists in the database.</errorMessage>" On ASAP that error code corresponds to "does not match format string" Do you know if the error messages list has been updated on the NE? Attached you can find the work order logs. | MEDIUM | Prakash | FINISHED
Switch request failures on JAM - SIMA connection issue to be investigated by IPvision. | 2018-05-29 | asap.support | 2018-05-29 | I verified the order and it was related to a missing parameter, but when i queried the subscriber, this and all of the requests targeting SIMA IPVISION are being responded with an error message. IPVISION SIMA NE is responding with a database connection error: | MEDIUM | Harish, Prakash | FINISHED
Additions for JAM's DN_RANGE Table | 2018-05-29 | asap.support | 2018-05-29 | Hi Neilsa; These are the dn ranges currently on the table: | LOW | Neilsa | FINISHED
Switch Failure | 2018-05-29 | asap.support | 2018-05-29 | Yesterday, SAIF module worked with some connection issues due to some network intermittence (from 11 hrs. to 15 hrs), once we verified connection towards SAIF was ok, we disabled Request Handler's connection device and assigned it to a new Activation session to restart load processing. | LOW | Kishore, Shalana | FINISHED
2018052504312932 | 2018-05-29 | asap.support | 2018-05-29 | the actual error retrieved from NE is "<errorCode>473</errorCode><errorMessage>PIN already exists in the database.</errorMessage>" On ASAP that error code corresponds to "does not match format string" Do you know if the error messages list has been updated on the NE? Attached you can find the work order logs. | MEDIUM | Praneetha | FINISHED
2018052504312853 | 2018-05-29 | asap.support | 2018-05-29 | the actual error retrieved from NE is "<errorCode>473</errorCode><errorMessage>PIN already exists in the database.</errorMessage>" On ASAP that error code corresponds to "does not match format string" Do you know if the error messages list has been updated on the NE? Attached you can find the work order logs. | MEDIUM | Praneetha | FINISHED
JAM switch request failures | 2018-05-29 | asap.support | 2018-05-29 | The SIMA part on the WO 181481495 was completed. The second request 181482531 failed in the DMS100 plaform. | LOW | Harish, Prakash | FINISHED
Liberate Incident: 244757,-- Switch Failure for Reconnection od Services. | 2018-05-29 | asap.support | 2018-05-30 | None of those numbers are provisioned in CAY_GNBND. Please add into the platform before to execute any change. | LOW | Mounika | FINISHED
JAM - POTS / SIMA request issues | 2018-05-31 | asap.support | 2018-05-31 | According to the following Activation plan table, SIMA Cartridge developer gave a greater precedence(weight) to SIMA commands. Actual error code is 1024: Cant find Service Class. | MEDIUM | Prakash | FINISHED
JAM - Urgent - Fixed line DMS and SONUS ASAP requests failing with TIMEOUT error | 2018-05-31 | asap.support | 2018-05-31 | JAM_SNS2 and JAM_SNS1 are not reachable from ASAP server jamu66, orders for other NEs should de be processing now, and please retry timed out orders. SONUS server is currently reachable only from ASAP wass1133 server. | MEDIUM | Prakash | FINISHED
Update on "SAPC Fix" wrt JAM | 2018-05-31 | asap.support | 2018-05-31 | SAPC cartridge service model contains now validation for sum volume limit RM to be executed when ROAM_FLAG equals to 1 or 2. | MEDIUM | Neilsa | FINISHED
LIME- ASAP- SIMA Add credit fails with SIMA_MISSING_PARAM | 2018-05-31 | asap.support | 2018-05-31 | yes we can set it as default. I'll modify it, test it and let you know the results. | MEDIUM | Juan Pablo | FINISHED
LIME- API- SIMA API ISSUES WHEN MODIFY A SUBSCRIBER - CaseID: 9231 | 2018-06-01 | asap.support | 2018-06-01 | Before the modifySubscriber service is invoked, a query to the subscriber is performed and the retrieved values are used to populate the modify or add credit request: I can set it as default value. But if subscriber exists and that value is set, then that retrieved value is set for the modify request. | MEDIUM | Prakash | OPEN
Mobile Switch Down | 2018-06-01 | asap.support | 2018-06-01 | we are verifying connections to ASAP. If there are hung connections we'll remove them and force new Activation sessions to start. SONUS requests are timing out as the SNS server is not reachable from jamu66. | LOW | Kishore | FINISHED
JAM - DMS POTS switch requests failing with Information not found in NEP data base error | 2018-06-04 | asap.support | 2018-06-04 | Discrepancies between the NE_ID in Liberate and those in ASAP. Due to either obsolete data in ASAP or a subrange being associated with more than 1 NE_ID. | MEDIUM | Neilsa | OPEN
Calls In suspense - Review Cease Requests at Switch | 2018-06-04 | asap.support | 2018-06-04 | CURRENT CONFIGURATIONS | MEDIUM | Joy | FINISHED
LIME- API- SIMA API ISSUES WHEN MODIFY A SUBSCRIBER - CaseID: 9231 | 2018-06-04 | asap.support | 2018-06-05 | Here's an example of the requests ASAP is sending to SIMA IPVISION: | LOW | Juan Pablo | FINISHED
CCN Request - 4456 : Postpaid Mobile Internet- Flow Lyf and Flow Platinum update - JAM [LIBERATE] | 2018-06-05 | asap.support | 2018-06-05 | Hello Praneetha; Yes, there is a problem with certain subscribers and the parameter combination of VOLUME_LIMIT and BOLT_ON_FLAG. We're verifying if this is a configuration issue or if it is an implementation failure. We'll let you know the result of the analysis and how to fix it. (SAPC) | MEDIUM | Praneetha | AWAITING RESPONSE IF THE FIX IS WORKING
2018053104323960 | 2018-06-05 | asap.support | 2018-06-08 | completed successfully now. | MEDIUM | Mounika | FINISHED
2018060404331048 | 2018-06-06 | asap.support | 2018-06-06 | The account name michaelbishop does not exist in the platform GND_ZBRA INFO ASDL Exit (ZIMBRA_DOESNOTEXIST) Msg : Cannot located user; Application attempted an operation on a user that does not exist. Please, Contiinue with the deletion with the POTS_DEL_SINGLE_LINE | LOW | Mounika | FINISHED
2018053104325056 | 2018-06-05 | asap.support | 2018-06-08 | completed successfully now. | MEDIUM | Mounika | FINISHED
2018060404330847 | 2018-06-05 | asap.support | 2018-06-08 | Completed successfully on resubmisssion. | MEDIUM | Samantha | FINISHED
2018060404330766 | 2018-06-05 | asap.support | 2018-06-08 | Completed successfully | MEDIUM | Samantha | FINISHED
Failed rosb / 9574152 / Lighthouse Resorts Ltd | 2018-06-07 | asap.support | 2018-06-07 | JAM_NGRLW 8769573000 8769574999 19801999 | LOW | Neilsa | FINISHED
Lookup Parameters for the DN_RANGE Table? | 2018-06-07 | asap.support | 2018-06-07 | both the 10-digit DN and the NE_ID select submcli from tbl_dnrange_submcli where 8766014395 between from_dn and to_dn and submcli = 'JAM_GRN1' | LOW | Neilsa | FINISHED
Additional DN_RANGE Table Rows for JAM_EAS1 | 2018-06-07 | asap.support | 2018-06-07 | Done | LOW | Neilsa | FINISHED
Additional DN_RANGE Table Rows for JAM_OCHO | 2018-06-07 | asap.support | 2018-06-07 | Done | LOW | Neilsa | FINISHED
Additional DN_RANGE Table Rows for JAM_PMBK | 2018-06-07 | asap.support | 2018-06-07 | Done | LOW | Neilsa | FINISHED
Additional DN_RANGE Table Rows for JAM_MOBY | 2018-06-07 | asap.support | 2018-06-07 | Done | LOW | Neilsa | FINISHED
Modified DN_RANGE Table Rows for JAM_CRC% | 2018-06-07 | asap.support | 2018-06-07 | Done | LOW | Neilsa | FINISHED
2018061404348976 | 2018-06-14 | asap.support | 2018-06-14 | Order 182549943 timed out on ASAP. It could not start session with SONUS NE. | LOW | Mounika | FINISHED
2018061404349316 | 2018-06-15 | asap.support | 2018-06-15 | The Work Order 182578367 timed out on ASAP. It could not start session with SONUS NE. The issue was reported. We will let you know when all those requests can be resubmitted. | LOW | Mounika | FINISHED
2018061404350216 | 2018-06-15 | asap.support | 2018-06-15 | Do you have a command number or switch message related to this service number? | LOW | Mounika | FINISHED
2018061804356250 | 2018-06-19 | asap.support | 2018-06-19 | Work order command number 182717063 includes a request to CMV_MOBY NE, and CMV_MOBY has been decommissioned. | LOW | Mounika | FINISHED
Liberate Incident: 244901 | 2018-06-18 | asap.support | 2018-06-18 | Yes, we are working on set the error code as soft fail, as soon as we finished we'll let you know.
2018061804356250 | 2018-06-19 | asap.support | 2018-06-19 | The Work order command number 182717063 includes a request to CMV_MOBY NE, and CMV_MOBY has been decommissioned. | LOW | Mounika | FINISHED
Prepaid Huawei (SIMA) service status. #6582950111 | 2018-06-19 | asap.support | 2018-06-19 | Work order failed when it reached the atomic service for SIMA request: | LOW | Suresh | FINISHED
Liberate: Incident: 245112 Limeref:4332533 SUSPENSE-INVALID CALLING NUMBER - ANU | 2018-06-19 | asap.support | 2018-06-19 | Could you please provide us the related NE to those service numbers, to verify its existence on network level? (NEAX) | MEDIUM | Abhijit | AWAITING RESPONSE FROM LIBERATE
Determining Add't 876 Ranges Needed for JAM's Largest Exchanges | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
Additional DN_RANGE Table Rows for JAM_MOBY | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_CAR3 | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_CENT | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_BRA4 | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_EAS1 | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_CARL | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_MDVL | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
MONA, MONT & WST2 | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_MONA | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_WST2 | 2018-06-20 | asap.support | 2018-06-20 | Done | LOW | Neilsa | FINISHED
CWJ - SIMA - Credit should expire after 40 days - CaseID: 9265 | 2018-06-22 | asap.support | 2018-06-22 | Done | LOW | Juan Pablo | FINISHED
LIME - SIMA - Normalize PINS and Subscribers IDs -CaseID:9264 | 2018-06-22 | asap.support | 2018-06-22 | Done | LOW | Juan Pablo | FINISHED
Prepaid Huawei (SIMA) service status. #8769735032 | 2018-06-21 | asap.support | 2018-06-21 | Done | LOW | Suresh | FINISHED
Additional DN_RANGE Table Rows for JAM_MOBY | 2018-06-22 | asap.support | 2018-06-22 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_CAR3 | 2018-06-22 | asap.support | 2018-06-22 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_MDVL | 2018-06-22 | asap.support | 2018-06-22 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table Rows for JAM_MYPN | 2018-06-22 | asap.support | 2018-06-22 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_ROSE | 2018-06-22 | asap.support | 2018-06-22 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_PTMR | 2018-06-22 | asap.support | 2018-06-22 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_OCHO | 2018-06-22 | asap.support | 2018-06-22 | Done | LOW | Neilsa | FINISHED
2018062204364449 | 2018-06-25 | asap.support | 2018-06-25 | We've obtained destination susbcriber's information and it was stored in SIMA with invalid expiration and suspension dates: | LOW | Mounika | FINISHED
Liberate: Incident: 245112 Limeref:4332533 SUSPENSE-INVALID CALLING NUMBER - ANU | 2018-06-25 | asap.support | 2018-06-25 | Liberate support, Rosaline , we are not able to map the EXCH_ID (provided in the EXCEL file) to the known NE_ID. We required the NE_ID parameter used in the switch message. Is it possible to provide us the NE_ID for each service number? | LOW | Rosaline | FINISHED
ASAP ticket number 4367418 | 2018-06-25 | asap.support | 2018-06-25 | Hi Kishore, this ticket request was investigated and solved with the database synchronization. Please let us know if the fix is working. Thanks in advance. | MEDIUM | Kishore | FINISHED
Aria slow and Liberate switch issues (SR2535946) | 2018-06-26 | asap.support | 2018-06-26 | Database out of line | MEDIUM | Shalana | FINISHED
DN_RANGE Table for JAM_CHN1 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_EAS2 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_DSB1 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_BTWN, JAM_BOGE and JAM_BLBY | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_LLP2 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_LRTV | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_NWBN | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_NGRL | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_MOBY | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_RDGD | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_WSH3 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_NGRV | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_FLMH | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_SPL1 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_WST2 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
ASAP-jamu66-database time- Delays in the starting of orders processing | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_CRGD | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_GNWD | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_GRHL | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_GRN1 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_HPWL | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_JMH2 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_JNC1 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_LGVL | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_LNMT | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_ROSE | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_PTMR | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_PMBK | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_MYPN | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_MONA | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_MDVL | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_CENT | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_CHAT | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_CLTN | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_CMBG | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_DGPT | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_DSB1 | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_ELTH | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_ERTN | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_MONT | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED
DN_RANGE Table for JAM_OCHO | 2018-06-26 | asap.support | 2018-06-26 | Done | LOW | Neilsa | FINISHED

## ACUT oldies (hidden)
TICKET |  | Alias | Status | Report Title - Record ID | Response
2016042102835163 | Zoé | 2835163 | New | LIBERATE SWITCH ERROR0-URGENT DORETHA.SNAGG@TIME4LIME.COM 4-Medium | The order was not found on ASAP's servers The Specified MSISDN is already definedThe Specified MSISDN is already defined with a different IMSI IT Service Assurance, Please transfer this to liberate to validate the correct procedure for the restoration of this account.
2016042202837599 | Zoé | 2837599 | Transferred to Resolving Group | STALLED TRANSACTIONS VIA ASAP FSELMAN@CWC.COM | The orders were not found on ASAP's servers IT Service Assurance, Please transfer this to liberate to validate if it is required the resubmission of this transactions.
2016042202838091 | Zoé | 2838091 | New | SERVICE RESTORATION FAILED AT SWITCH 246 4165678 ROBERTA.ADAMS@LIME.COM 4-Medium | The order was not found on ASAP's servers IT Service Assurance, Please transfer this to liberate to validate the correct procedure for the restoration of this account.
2016042502841736 | Zoé | 2841736 | New | CONTACT CENTRE TIMED OUT SWITCH REQUEST NATHTOYA.SCARLETT@LIME.COM 4-Medium | IT Service Assurance, Please transfer this to liberate to validate if it is required the resubmission of this transaction.
2016042502843067 | Zoé | 2843067 | New | ROSB FAILING SHANIQUE.WILLIAMS@LIME.COM 4-Medium | IT Service Assurance, Please transfer this to liberate to validate if it is required the resubmission of this transaction.
2016050102855686 | Zoé | 2855686 | New | SWITCH FAILURE SASHINE.HOWELL@TELUSINTERNATIONAL.COM
2016050102855687 | -- | 2855687 | New | SWITCH FAILURE SASHINE.HOWELL@TELUSINTERNATIONAL.COM 4-Medium
2016050302857575 | -- | 2857575 | New | LIBERATE GETTING ISSUES WITH COMMANDS WHILE PROVISIONING CALL FEATURE "MWT (MESSAGE WAITING)". ROHAN.KURVE@IGATE.COM 4-Medium
2016050302858372 | -- | 2858372 | New | UNABLE TO RESTORE A/C SHANIQUE.WILLIAMS@LIME.COM 4-Medium
2016050402860309 | Zoé | 2860309 | New | SWITCH FAILURE LIBERATE JEVENE.MCCALLUM@TELUSINTERNATIONAL.COM | IT Service Assurance, Please transfer this to liberate to validate if it is required the resubmission of this transaction.
2016050402862673 | Zoé | 2862673 | New | SWITCH FAILURE SASHINE.HOWELL@TELUSINTERNATIONAL.COM 4-Medium | IT Service Assurance, Please transfer this to liberate to validate if it is required the resubmission of this transaction.
2016060102920366 |  |  |  | create a ticket to Felita | "IT Service Assurance Could you please log a ticket and then assign it to Felita Selman of Barbados' Fixed-lien MDF team. The ticket is because the BAR_SLVR is sending the WO's to abort."
2016051502884758 | Zoé | 2884758 | New | TEST SITE1 NAME SWITCH FAILURE SASHINE.HOWELL@TELUSINTERNATIONAL.COM 4-Medium | <Answer on e-mail>
2016051502884761 | Zoé | 2884761 | New | TEST SITE1 NAME SWITCH FAILURE SASHINE.HOWELL@TELUSINTERNATIONAL.COM 4-Medium | <Answer on e-mail>
2016051502884882 | Zoé | 2884882 | New | TEST SITE1 NAME SWITCH FAILURE SASHINE.HOWELL@TELUSINTERNATIONAL.COM 4-Medium | IT Service Assurance, Please transfer this incident to Felita Selman of Barbados' Fixed-lien MDF team.
2016051702888588 | Zoé | 2888588 | New | ROSB FAILING - PLEASE RECONNECT SERVICE SHANIQUE.WILLIAMS@LIME.COM 4-Medium | <Answer on e-mail>
2016052002894388 | Zoé | 2894388 | New | CONTACT CENTRE RESTORATION SWITCH FAILURE ROST 8764355567 LATOYA.BRYAN@LIME.COM 4-Medium | <Answer on e-mail>
2016052402903078 | Zoé | 2903078 | New | SWITCH FAILURE SASHINE.HOWELL@TELUSINTERNATIONAL.COM 4-Medium | <Answer on e-mail>
2016052702910281 | Mónica | 2910281 | New | SWITCH FAILURE JEVENE.MCCALLUM@TELUSINTERNATIONAL.COM 4-Medium | <Answer on e-mail>
2016052902912238 | Mónica | 2912238 | New | SWITCH FAILURE SASHINE.HOWELL@TELUSINTERNATIONAL.COM 4-Medium | <Answer on e-mail>

## REFUSED CONNECTION
CONNECTION REFUSE E-MAIL TITLE | DATE | STATUS
ASAP monitor; connection refused SLU_UVF | 2018-01-24 | CLOSED
ASAP monitor; connection refused EST_GSAT & EST_GSAT1 | 2018-01-25 | OPEN
ASAP monitor; connection refused SLU_UVF | 2018-01-30 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-02-02 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-02-05 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-02-06 | CLOSED
ASAP monitor; connection refused SLU_CEN | 2018-02-05 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-02-09 | CLOSED
ASAP monitor; connection refused JAM_CALIX | 2018-02-13 | OPEN
ASAP monitor; connection refused SLU_UVF | 2018-02-16 | CLOSED
ASAP-WASS133-ASAP There is no connection to Database -No Listener | 2018-02-18 | CLOSED
ASAP JAMU66 shutdown | 2018-02-22 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-02-22 | CLOSED
ASAP monitor; connection refused CAY_GNBND with WASS1133 | 2018-02-22 | OPEN
ASAP monitor; connection refused SLU_UVF | 2018-02-22 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-02-28 | CLOSED
WASS1133-ASAP provisioning asappro1 user fails to login | 2018-02-28 | CLOSED
ASAP monitor; connection refused SLU_CEN | 2018-03-05 | CLOSED
JAM_MOBY connection failure | 2018-03-09 | CLOSED
ASAP-FLOW-monitor, Unable to connect to remote host: Connection refused to SLU_UVF | 2018-03-13 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-03-14 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-03-28 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-04-02 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-04-03 | CLOSED
ASAP monitor; connection refused JAM_EAST | 2018-04-03 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-04-05 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-04-09 | CLOSED
ASAP connection refused SONUS | 2018-04-11 | CLOSED
ASAP connection refused SONUS | 2018-04-16 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-04-16 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-04-26 | CLOSED
ASAP monitor; connection refused SLU_CEN | 2018-04-26 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-04-30 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-05-02 | CLOSED
LIME-ASAP-jamu66-Connection Fail to SONUS platform | 2018-05-28 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-06-11 | CLOSED
ASAP monitor; connection refused SLU_UVF | 2018-06-11 | CLOSED
ASAP monitor; connection refused SLU_UVF and SLU_CEN | 2018-06-19 | CLOSED
ASAP monitor; connection refused SLU_UVF and SLU_CEN | 2018-06-21 | CLOSED
ASAP-Route Activation traffic to wass1133 | 2018-06-24 | CLOSED

## RFC SUPPORT
CONCEPT | DATE
RFC 4080434 - Barbados HLR CP Upgrade from R12B to R15A | 2018-01-25
¦RFC6786¦ SCHEDULED RFC NOTIFICATION Cleandata Routine Maintenance on JAMU66 | 2018-02-22
RFC6955-Reroute provisioning on Barbados HLR to Jamaica HLR - MW3 | 2018-03-07
¦RFC7430¦ SCHEDULED RFC NOTIFICATION Routine Maintenance: ASAP Cleandata on JAMU66 server | 2018-04-11
¦RFC8041¦ SCHEDULED RFC NOTIFICATION ASAP Cleandata Maintenance Activity - JAMU66 | 2018-05-24

## QUEUES (hidden)
FLOW IT AUTOMATED PROVISIONING
ABS
ANTIGUA IT
ANTIGUA SERVICE SUPPORT DELIVERY BUILDING MTNCE
ANTIGUA SERVICE SUPPORT DELIVERY SECURITY
BAR FINANCE BILLING AND RA
BARBADOS SERVICE SUPPORT DELIVERY BUILDING MNTCE
BARBADOS SERVICE SUPPORT DELIVERY DESK/LAN/ASSET
BCGI
BUSINESS ANALYST
BUSINESS CONTINUITY RISK MANAGEMENT
BUSINESS CONTROL
BUSINESS SOLUTIONS
CALL CENTRE
CALL CENTRE AGENT
CALL CENTRE CUSTOMER ASSURANCE
CALL CENTRE EMAIL
CAMPAIGN MANAGER (BLS)
CAPACITY MANAGEMENT ENGINEERING
CAPITAL PROGRAMMES
CARRIER SERVICES SERVICE MANAGEMENT
CAYMAN IT DESKTOP SUPPORT
CC ACTIVATION AND BILLING BSS
CHANGE MANAGEMENT
CIS SUPPORT (LONDON)
COMVERSE LIMEWARE & DIGITAL ROUTE
COMVERSE ONE RT
COMVERSE ONE TIER ONE
COMVERSE PCAT CONFIGURATION
COMVERSE TESTING
COMVERSE VAS SUPPORT
CSC_T1
CSC_T2
CSGI INTERCONNECT SUPPORT SERVICES
CSGI MEDIATION SUPPORT SERVICES
CSGI RETAIL MEDIATION SUPPORT SERVICES
CSGI WHOLESALE MEDIATION SUPPORT SERVICES
CUSTOMER MGMT SALESFORCE SYSTEM
CUSTOMER MOBILE
CUSTOMER PORTAL SUPPORT
CUSTOMER SOLUTIONS DELIVERY
DOLPHIN
ENTERPRISE SOLUTIONS - BUSINESS INTELLIGENCE
ENTERPRISE SOLUTIONS - DATABASE MANAGEMENT
ENTERPRISE SOLUTIONS - ENHANCED SERVICES
ENTERPRISE SOLUTIONS - GROUPWARE
ENTERPRISE SOLUTIONS - HR AND PAYROLL
ERICSSON ANGUILLA MOBILE
ERICSSON ANTIGUA SSD
ERICSSON BARBADOS SSD (MOBILE)
ERICSSON BVI SSD (MOBILE)
ERICSSON CAYMAN SSD
ERICSSON CHANGE MANAGEMENT
ERICSSON DOMINICA MOBILE
ERICSSON GRENADA MOBILE
ERICSSON ISP DATA
ERICSSON IT PROVISIONING SERVICES
ERICSSON JAMAICA SSD (MOBILE)
ERICSSON JAMAICA SSD (POWER)
ERICSSON LIME MANAGED USER ACCESS
ERICSSON MOBILE CIRCUIT CORE
ERICSSON MOBILE OPTIMIZATION SUPPORT
ERICSSON MOBILE OSS-RC
ERICSSON MOBILE PACKET CORE
ERICSSON MOBILE PBN
ERICSSON MOBILE RAN
ERICSSON MOBILE SSD HOLDING
ERICSSON MOBILE VAS
ERICSSON PROBLEM MANAGEMENT
ERICSSON ST KITTS & NEVIS - MOBILE
ERICSSON ST LUCIA MOBILE
ERICSSON ST VINCENT MOBILE
ERICSSON TURKS MOBILE
FAULT MANAGEMENT CENTER
FIXED ENGINEERING
FLOW FOR THE Q
FLOW ANGUILLA - NETWORK OPS
FLOW ANTIGUA - FACILITIES & FLEET
FLOW ANTIGUA - FIXED & BROAD BAND
FLOW ANTIGUA - IP & DATA
FLOW ANTIGUA - POWER
FLOW ANTIGUA - TRANSMISSION
FLOW BARBADOS - EXTERNAL PLANT
FLOW BARBADOS - FIXED
FLOW BARBADOS - Field Services
FLOW BARBADOS - IP AND DATA
FLOW BARBADOS - MDF
FLOW BARBADOS - POWER
FLOW BARBADOS - TRANSMISSION
FLOW CAYMAN SSD
FLOW DOMINICA - EXTERNAL PLANT
FLOW DOMINICA - FIXEDFLOW DOMINICA - FIXED
FLOW DOMINICA - IP & DATA
FLOW DOMINICA - POWER
FLOW DOMINICA - ROUTINES
FLOW FIXED PLATFORM BROADBAND SUPPORT
FLOW FIXED PLATFORM VOICE SUPPORT
FLOW GRENADA SERVICE SUPP DEL MTNCE
FLOW GRENADA SSD
FLOW IT ASSURANCE SERVICES
FLOW IT OSS MONITORING
FLOW IT POINT OF SALES SUPPORT
FLOW JAMAICA DISPATCH CENTER | Network tickets only.
FLOW JAMAICA EXTERNAL PLANT
FLOW JAMAICA SSD (FIXED)
FLOW JAMAICA SSD (IP & DATA)
FLOW JAMAICA SSD (MOBILE)
FLOW JAMAICA SSD (POWER)
FLOW MPLS AND INTERNET CORE
FLOW PROBLEM MANAGEMENT
FLOW RNOC TIER 1
FLOW SOC-T2
FLOW ST KITTS - DESKTOP SUPP
FLOW ST KITTS - FACILITIES & FLEET
FLOW ST KITTS - FIXED & BROAD BAND
FLOW ST KITTS - IP & DATA
FLOW ST KITTS - OSP
FLOW ST KITTS - POWER
FLOW ST LUCIA - CUST EXP B2B
FLOW ST LUCIA - CUST EXP CONSUMER
FLOW ST LUCIA - DESKTOP SUPPORT
FLOW ST LUCIA - FACILITIES
FLOW ST LUCIA - NETWORK OPS
FLOW ST LUCIA - OSP
FLOW ST LUCIA - ROUTINES
FLOW ST VINCENT - DESKTOP SUPP
FLOW ST VINCENT - OSP
FLOW ST VINCENT - POWER-FACILITIES & FLEET
FLOW ST VINCENT - TRANS-FIXED-BBAND-IPD
FLOW TRANSMISSION (DOMESTIC) SUPPORT
FLOW TRANSMISSION OPTMIZATION
FLOW TURKS - CUSTOMER EXPFLOW TURKS - NETWORK OPS
Facey/EMIDA
Fraud Barring
HOLD - Holding
HP SUPPORT
IGATE LIBERATE CONFIGURATION
IGATE LIBERATE TIER 2 SUPPORT
IKANO COMMUNICATIONS
IMS SUPPORT
INFRASTRUCTURE - CLOUD SERVICES
INFRASTRUCTURE - FIREWALL AND ENTERPRISE NETWORK
INFRASTRUCTURE - NETWORK MANAGEMENT
INFRASTRUCTURE - SERVER PLATFORM
INNOVAPPTIVE
INVENTORY AND CONFIGURATION MANAGEMENT
IP AND TRANSMISSION ENGINEERING
IT BILLING OPERATIONS
IT BILLING RATING MEDIATION - ROAMING SERVICES
ITELLIGENCE
IVR TELECONFERENCE SUPPORT
JAM CUSTOMER SUPPORT TAC
JAMAICA IT DESKTOP SUPPORT
JAMAICA SERVICE SUPP DELIVERY BUILDING MAINTENANCE
JAMAICA SERVICE SUPPORT AND DELIVERY (LAN)
JAMAICA SERVICE SUPPORT DELIVERY SECURITY ALERTS
JAMAICA SERVICE SUPPORT OPERATIONS(NETWORK)
LEAM JAMAICA
LIME BVI SSD (DESKTOP SUPPORT)
LIME BVI SSD (FACILITIES & FLEET)
LIME BVI SSD (FIXED)
LIME BVI SSD (IP & DATA)
LIME BVI SSD (OSP)
LIME BVI SSD (TRANS)
LIME RETAIL MANAGERS
LIME ROAMING FAULT SUPPORT
MOBILE AWARE
MOBILE ENGINEERING
MOBILE SERVICE SUPPORT
MONTSERRAT SERVICE SUPPORT AND DELIVERY
MOORES SUPPORT
MOREMAGIC SUPPORT
NET2PHONE
NETWORK SERVICES ARCHITECTURE
Numero Vendor Support
One Ticket Portal Users(DO NOT USE)
PERSONNEL SERVICES
POWER ENGINEERING
PRINTER SUPPORT
PROGRAMME MANAGEMENT OFFICE
PROJECT MGMT-NORTHERN CLUSTER
PROV TESTERS
REGIONAL PAYMENTS
SAP 3RD LEVEL SUPPORT
SAP COMPETENCY CENTRE
SERVICE MANAGEMENT
SKILLSOFT SUPPORT
SLU OUTSIDE PLANT MAINTENANCE AND INSTALLATIONS
SSL DOMAIN AND SHAREPOINT SUPPORT
TECHNOLOGY OPERATIONS
TECHNOLOGY OPERATIONS ASSURANCE
TECHNOLOGY OPERATIONS FIXED AND BROADBAND
TECHNOLOGY OPERATIONS IP AND DATA
TECHNOLOGY OPERATIONS MOBILE
TECHNOLOGY OPERATIONS TRANSMISSION
TECHNOLOGY OPERATIONS TV POLICY AND CONTENT
TECHNOLOGY PLANNING
TECHNOLOGY SERVICE DESK
THIRD PARTY VENDOR
TIER 1 NOC
TNZI ISSC
TRANSMISSION PLATFORM DESIGN ENGINEERING
TRANSMISSION PLATFORM INTERNATIONAL
TURKS AND CAICOS SERVICE SUPPORT DELIVERY BLDG MTN
TURKS AND CAICOS SERVICE SUPPORT DELIVERY SECURITY
TV POLICY AND CONTENT ENGINEERING
VERAZ SUPPORT
VIRTACORE
VOXGEN
WESTERN UNION
XACTLY